## S2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | 02. Product Management | 02.01 | Create Product | Research and select a form handling library/API | 2024-10-29 | 2024-10-29 | 100% | Sai Vyshnav Ananthula
2 | 02. Product Management | 02.01 | Create Product | Implement form to capture product details | 2024-10-29 | 2024-10-29 | 100% | Sai Vyshnav Ananthula
3 | 02. Product Management | 02.01 | Create Product | Add fields for "Brand," "Title," "Color," "Price," etc. | 2024-10-30 | 2024-10-30 | 100% | Sai Vyshnav Ananthula
4 | 02. Product Management | 02.01 | Create Product | Implement "Add New Product" submission functionality | 2024-10-30 | 2024-10-30 | 100% | Deepak Kumar Dhullipala
5 | 02. Product Management | 02.01 | Create Product | Display confirmation message upon successful creation | 2024-10-31 | 2024-10-31 | 100% | Deepak Kumar Dhullipala
6 | 02. Product Management | 02.01 | Create Product | Test Create Product functionality | 2024-10-31 | 2024-10-31 | 100% | Deepak Kumar Dhullipala
6 | 02. Product Management | 02.02 | Delete Product | Implement deletion API to remove products from the database | 2024-11-01 | 2024-11-01 | 100% | Priyanshu Rastogi
7 | 02. Product Management | 02.02 | Delete Product | Display product information (image, title, category, price, quantity) along with a delete button. | 2024-11-02 | 2024-11-02 | 100% | Priyanshu Rastogi
8 | 02. Product Management | 02.02 | Delete Product | Implement core deletion functionality and ensure seamless integration with the backend | 2024-11-03 | 2024-11-03 | 100% | Priyanshu Rastogi
9 | 02. Product Management | 02.02 | Delete Product | Design and implement GUI elements such as the delete button and confirmation prompts. | 2024-11-04 | 2024-11-04 | 100% | Lokesh Adusumalli
10 | 02. Product Management | 02.02 | Delete Product | Test delete functionality to ensure products are correctly removed and verify error handling. | 2024-11-05 | 2024-11-05 | 100% | Lokesh Adusumalli
11 | 02. Product Management | 02.04 | Product Categories | Research hierarchical category structure best practices | 2024-11-06 | 2024-11-06 | 100% | Yeswanth Sai Bezawada
12 | 02. Product Management | 02.04 | Product Categories | Implement dropdowns for category selection | 2024-11-07 | 2024-11-07 | 100% | Yeswanth Sai Bezawada
13 | 02. Product Management | 02.04 | Product Categories | Add "Top Level," "Second Level," and "Third Level" categories | 2024-11-08 | 2024-11-08 | 100% | Yeswanth Sai Bezawada
11 | 02. Product Management | 02.04 | Product Categories | Style category selection fields for user-friendly display | 2024-11-09 | 2024-11-09 | 100% | Nikunj Ramnikbhai chavda
12 | 02. Product Management | 02.04 | Product Categories | Test Product Categories functionality | 2024-11-10 | 2024-11-10 | 100% | Nikunj Ramnikbhai chavda
13 | 02. Product Management | 02.05 | Filter Products By Attributes | Implement filtering API to fetch products based on attributes | 2024-11-11 | 2024-11-11 | 100% | Rithika Gongalla
14 | 02. Product Management | 02.05 | Filter Products By Attributes | Display products based on selected filters (e.g., color, size) | 2024-11-12 | 2024-11-12 | 100% | Rithika Gongalla
15 | 02. Product Management | 02.05 | Filter Products By Attributes | Implement core filtering functionality for product attributes | 2024-11-13 | 2024-11-13 | 100% | Rithika Gongalla
16 | 02. Product Management | 02.05 | Filter Products By Attributes | Design and implement GUI elements for attribute filtering | 2024-11-14 | 2024-11-14 | 100% | Susmitha Kurra
17 | 02. Product Management | 02.05 | Filter Products By Attributes | Test filtering functionality across various attribute options | 2024-11-15 | 2024-11-15 | 100% | Susmitha Kurra
18 | 02. Product Management | 02.06 | Navigate Product Listings With Pagination | Display products based on selected page | 2024-11-16 | 2024-11-16 | 100% | Avinash Sura
19 | 02. Product Management | 02.06 | Navigate Product Listings With Pagination | Implement core pagination functionality | 2024-11-17 | 2024-11-17 | 100% | Avinash Sura
20 | 02. Product Management | 02.06 | Navigate Product Listings With Pagination | Implement GUI requirements for pagination | 2024-11-18 | 2024-11-18 | 100% | SaidivyaSree Budagam
21 | 02. Product Management | 02.06 | Navigate Product Listings With Pagination | Test pagination functionality across pages | 2024-11-19 | 2024-11-19 | 100% | SaidivyaSree Budagam

## S3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | 02. Product Management | 02.03 | Product Reviews | Create a UI for the review page to display products ordered | 2024-11-19 | 2024-11-19 | 100% | Sai Vyshnav Ananthula
2 | 02. Product Management | 02.03 | Product Reviews | Add functionality to allow users to provide ratings for products | 2024-11-20 | 2024-11-20 | 100% | Sai Vyshnav Ananthula
3 | 02. Product Management | 02.03 | Product Reviews | Implement a text box for users to write product reviews | 2024-11-21 | 2024-11-21 | 100% | Sai Vyshnav Ananthula
4 | 02. Product Management | 02.03 | Product Reviews | Ensure the "Rate & Review Product" button links to the review form. | 2024-11-22 | 2024-11-22 | 100% | Sai Vyshnav Ananthula
5 | 02. Product Management | 02.03 | Product Reviews | Integrate backend APIs to save and fetch reviews for each product | 2024-11-23 | 2024-11-23 | 100% | Deepak Kumar Dhullipala
6 | 02. Product Management | 02.03 | Product Reviews | Produce Test Design Specification | 2024-11-24 | 2024-11-24 | 100% | Deepak Kumar Dhullipala
7 | 02. Product Management | 02.03 | Product Reviews | Produce Test Case Specification | 2024-11-24 | 2024-11-24 | 100% | Deepak Kumar Dhullipala
8 | 02. Product Management | 02.03 | Product Reviews | Perform Testing on reviews display | 2024-11-24 | 2024-11-24 | 100% | Deepak Kumar Dhullipala
9 | 03. Order Management | 03.01 | Add items to cart | Build the UI for the cart section to display selected items | 2024-11-25 | 2024-11-25 | 100% | Priyanshu Rastogi
10 | 03. Order Management | 03.01 | Add items to cart | Add functionality to update product quantity in the cart | 2024-11-26 | 2024-11-26 | 100% | Priyanshu Rastogi
11 | 03. Order Management | 03.01 | Add items to cart | Implement real-time updates to the price summary (subtotal, etc.) | 2024-11-27 | 2024-11-27 | 100% | Priyanshu Rastogi
12 | 03. Order Management | 03.01 | Add items to cart | Enable a "Remove" button for users to delete products from the cart | 2024-11-28 | 2024-11-28 | 100% | Priyanshu Rastogi
13 | 03. Order Management | 03.01 | Add items to cart | Integrate backend APIs to store, update, and retrieve cart data. | 2024-11-29 | 2024-11-29 | 100% | Rithika Gongalla
14 | 03. Order Management | 03.01 | Add items to cart | Produce Test Design Specification | 2024-11-30 | 2024-11-30 | 100% | Rithika Gongalla
15 | 03. Order Management | 03.01 | Add items to cart | Produce Test Case Specification | 2024-11-30 | 2024-11-30 | 100% | Rithika Gongalla
16 | 03. Order Management | 03.01 | Add items to cart | Perform Testing on cart display | 2024-11-30 | 2024-11-30 | 100% | Rithika Gongalla
17 | 03. Order Management | 03.03 | Accept/Reject Orders | Create a UI component to display all orders with details (e.g., title, price, ID, and status) | 2024-12-01 | 2024-12-01 | 100% | SaidivyaSree Budagam
18 | 03. Order Management | 03.03 | Accept/Reject Orders | Add buttons or dropdowns for admins to Accept or Reject orders | 2024-12-02 | 2024-12-02 | 100% | SaidivyaSree Budagam
19 | 03. Order Management | 03.03 | Accept/Reject Orders | Update the backend API to save the accepted/rejected status of an order | 2024-12-03 | 2024-12-03 | 100% | SaidivyaSree Budagam
20 | 03. Order Management | 03.03 | Accept/Reject Orders | Produce Test Design Specification | 2024-12-04 | 2024-12-04 | 100% | Lokesh Adusumalli
21 | 03. Order Management | 03.03 | Accept/Reject Orders | Produce Test Case Specification | 2024-12-04 | 2024-12-04 | 100% | Lokesh Adusumalli
22 | 03. Order Management | 03.03 | Accept/Reject Orders | Perform Testing on orders display | 2024-12-04 | 2024-12-04 | 100% | Lokesh Adusumalli
23 | 03. Order Management | 03.04 | Update Order Status | Add a dropdown or button to allow admins to update the status of an order (e.g., Confirmed, Shipped, Delivered) | 2024-12-05 | 2024-12-05 | 100% | Nikunj Ramnikbhai chavda
24 | 03. Order Management | 03.04 | Update Order Status | Integrate backend APIs to update the order status dynamically and save it in the database | 2024-12-06 | 2024-12-06 | 100% | Nikunj Ramnikbhai chavda
25 | 03. Order Management | 03.04 | Update Order Status | Add UI indicators for each status to reflect progress (e.g., color-coded labels for Pending, Shipped, etc.) | 2024-12-07 | 2024-12-07 | 100% | Yeswanth Sai Bezawada
26 | 03. Order Management | 03.04 | Update Order Status | Ensure status transitions follow logical rules (e.g., cannot skip from Pending to Delivered) | 2024-12-08 | 2024-12-08 | 100% | Yeswanth Sai Bezawada
27 | 03. Order Management | 03.04 | Update Order Status | Produce Test Design Specification | 2024-12-09 | 2024-12-09 | 100% | Yeswanth Sai Bezawada
28 | 03. Order Management | 03.04 | Update Order Status | Produce Test Case Specification | 2024-12-09 | 2024-12-09 | 100% | Yeswanth Sai Bezawada
29 | 03. Order Management | 03.04 | Update Order Status | Perform Testing on update order status display | 2024-12-09 | 2024-12-09 | 100% | Yeswanth Sai Bezawada
30 | 04. Finance Management | 04.01 | Process Payments | Research and integrate a suitable payment gateway/API | 2024-12-10 | 2024-12-10 | 100% | Susmitha Kurra
31 | 04. Finance Management | 04.01 | Process Payments | Implement functionality to calculate total price, including discounts and delivery charges | 2024-12-11 | 2024-12-11 | 100% | Susmitha Kurra
32 | 04. Finance Management | 04.01 | Process Payments | Add dynamic fields to display price breakdown (Price, Discount, Delivery Charges, Total Amount) | 2024-12-12 | 2024-12-12 | 100% | Susmitha Kurra
33 | 04. Finance Management | 04.01 | Process Payments | Implement functionality to update price details dynamically based on cart data | 2024-12-13 | 2024-12-13 | 100% | Susmitha Kurra
34 | 04. Finance Management | 04.01 | Process Payments | Design and implement "Check Out" button functionality | 2024-12-14 | 2024-12-14 | 100% | Susmitha Kurra
35 | 04. Finance Management | 04.01 | Process Payments | Validate payment and cart details before initiating the checkout process | 2024-12-14 | 2024-12-14 | 100% | Avinash Sura
36 | 04. Finance Management | 04.01 | Process Payments | Produce Test Design Specification | 2024-12-15 | 2024-12-15 | 100% | Avinash Sura
37 | 04. Finance Management | 04.01 | Process Payments | Produce Test Case Specification | 2024-12-15 | 2024-12-15 | 100% | Avinash Sura
38 | 04. Finance Management | 04.01 | Process Payments | Perform Testing on payment display | 2024-12-15 | 2024-12-15 | 100% | Avinash Sura