## StyleHive
USER STORIES - StyleHive
Module | Title | As a/an | I want to... | So that I can... | Sprint | Story Points | Story Constraints | Story Exceptions
01. User Management | 01.01 Create User Account | Guest user,Product Owner | create a user account | access and use the application's features | S1 | 4 | must produce a working e-mail address and password | if login fails, show a error message
| 01.02 Log into Account | Guest User, Registered User,Product Owner | secure authentication system implemented | can login to my account safely | S1 | 4 | Allow two-factor authentication using SMS and email | If the account is logged in from a new device, email the user.
| 01.03 Manage User Profile | Guest User, Registered User,Product Owner | securely recover or reset my lost or forgotten account credentials | regain access to my account | S1 | 4 | To obtain the reset link, the user must provide their registered phone number or email address. | If an account is locked after too many unsuccessful attempts at a reset, notify the user.
02. Product Management | 02.01 Create Product | Product Owner, Database Administrator | Create the product | deploy the product | S2 | 4 | product details must be accurate | if anything missing, show a fallback
| 02.02 Delete Product | Product Owner, Database Administrator | delete the product | delete the product | S2 | 4 | user must validate product details | if product linked to orders hold the deletion
| 02.03 Product Reviwes | User | review and rate products | help others purchase product with my reviews | S2 | 2 | user must authenticate before giving review | if already reviewd, prevent multiple submissions
| 02.04 Product Categories | Product Owner, Database Administrator | categorize the products | order the different categories of products | S2 | 2 | category data must validate | If category already exists, prevent duplication
03. Order Management | 03.01 Add items to cart | Guest User, Registered User,Product Owner | checking items and able to add to cart | add products to the cart | S3 | 4 | Cart should retain items across sessions | If session expires, prompt to log in again
| 03.02 Order Placement | Registered User,Product Owner | able to place orders seamlessly which or in cart | easily order the products | S3 | 4 | must include a secure authentication | if login fails, show a error message
| 03.03 Accepting/Rejecting Orders | Registered User,Product Owner | able to accept or reject orders which placed | accept and reject orders | S3 | 4 | must include a secure authentication | if login fails, show a error message
| 03.04 Update Order Status | Registered User,Product Owner | able to track the order status | easily check the updates and status of my orders | S3 | 4 | user must login to check order status | if order status not dislayed, show relevent message
0.4 Finance Management | 04.01 Process Payments | Registered User,Product Owner | make payments seamlessly and securely, utilizing user-friendly authentication methods | protect my financial information | S3 | 4 | transactions must adhere to PCI DSS guidelines. | If transaction fails, show an error message
| 04.02 Generate Invoices | Product Owner,Database Administrator, Financial Analyst | access and download invoices detailing transactions | recognize the expenses for which I am being charged | S3 | 3 | user must authenticate to manage or generate the invoices | if authentication fails, show a error message
| 04.03 Create Financial Reports | Registered User,Product Owner,Database Administrator | manage to create financial reports every quarter | check the growth of the bussiness accordingly | S3 | 2 | user must authenticate to generate the financial reports | if login fails, show relevant message
0.5 Advertisement | 05.01 Create Ad | Product Owner | watch the website's sponsored ads to gain access to a variety of material. | keep up to date on pertinent goods or services. | S3 | 4 | Ads need to be pertinent to the user's context and the site's content. | Don't display advertisements if the customer has a premium ad-free membership.
| 05.02 Update Ad | Product Owner | customize the marketing materials I get | receive pertinent information and deals that pique my interest. | S3 | 3 | user must post new ads for update ads | if ads not updating, show relevant message
| 05.03 Delete Ad | Product Owner | customize the marketing materials I get | receive pertinent information and deals that pique my interest. | S3 | 2 | user must login to delete the ad | if ads linked to any product, hold the deletion