## Road Map
StyleHive
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 10/22/2024 | SPRINT2 - 11/12/2024 | SPRINT3 - 12/10/2024
01. User Management | 01.01 Create User Account | 4 | X
| 01.02 Log into Account | 4 | X
| 01.03 Manage User Profile | 4 | X
02. Product Management | 02.01 Create Product | 4 |  | X
| 02.02 Delete Product | 4 |  | X
| 02.03 Product Reviews | 2 |  |  | X
| 02.04 Product Categories | 2 |  | X
| 02.05 Filter Products by attributes | 4 |  | X
| 02.06 Navigate Product Listings with Pagination | 4 |  | X
03. Order Management | 03.01 Add items to cart | 4 |  |  | X
| 03.02 Order Placement | 4
| 03.03 Accept/Reject orders | 4 |  |  | X
| 03.04 Update Order Status | 4 |  |  | X
04. Finance Management | 04.01 Process Payments | 4 |  |  | X
| 04.02 Generate Invoice | 3
| 04.03 Create Financial Reports | 2
05. Advertisement | 05.01 Create Ad | 4
| 05.02 Update Ad | 3
| 05.03 Delete Ad | 2
|  | VELOCITY: | 12 | 18 | 20